## Sheet1
PROJECT PLAN
Project Title | Zentra: An Integrated Multi-Platform for School Forms, Behavioral Documentation, and Alternative Delivery Mode with Rule-Based Early Intervention Detection at Mati School of Arts and Trades |  |  |  | START DATE | 2026-09-01
Project Members | Shekinah Jaljis, Reogie Akero Mabawad, Jeslito Geverola |  |  |  | END DATE | 2026-11-30
Adviser | Sir Alan Karl Gatdula |  |  |  | DAYS LEFT | 70 days
PROJECT OBJECTIVES
1. |  | To implement a digital SF10 management system that: 1.1 Receives SF10 forms and final grades/attendance from the Grading Portal. 1.2 Performs OCR extraction of the SF10 to store student data. 1.3 Centralizes searchable student permanent records and maintains version history and audit trails.
2. |  | To establish a secure anecdotal record management module that allows educators and counselors to document, categorize, and monitor student behavioral, academic, and emotional observations with strict role-based access and confidentiality controls.
3. |  | To develop an Alternative Delivery Mode (ADM) tracking system that: 3.1 Manages module distribution, submissions, and completion data. 3.2 Integrates performance into the grading portal, monitors deadlines, and participation in real time.
4. |  | To implement a rule-based early intervention detection system that: 4.1 Collects real-time data from grades, attendance, and anecdotal records. 4.2 Applies predefined thresholds to identify risk levels. 4.3 Classifies students into Low, Moderate, or High risk. 4.4 Provides recommended actions with staff approval. 4.5 Tracks intervention results.
5. |  | To implement an audit trail system that records all sensitive actions such as SF10 updates, grade locking, and anecdotal edits with user, timestamp, and reason.
6. |  | To generate comprehensive reporting and data visualization that aggregate data across modules to generate performance trends, intervention success rates, heat maps, and honor rolls.
WBS No. | PROJECT NAME |  | STATUS | START DATE | END DATE | DURATION | REMARKS
1.0 | System Architecture & Infrastructure |  | Done
1.1 | Supabase Auth & PostgreSQL Database Schema setup |  | Done | 2026-09-01 | 2026-09-05 | 5 days
1.2 | Define Rule-Based Early Intervention logic & thresholds |  | Done | 2026-09-06 | 2026-09-08 | 3 days
2 | Web Application Development |  | In Progress
2.1 | SF10 Management System & OCR extraction pipeline |  | In Progress | 2026-09-09 | 2026-09-20 | 12 days
2.2 | Web Grading Portal & Master Attendance registry |  | In Progress | 2026-09-21 | 2026-09-30 | 10 days
2.3 | Anecdotal Record Management with Role-Based Access |  | In Progress | 2026-10-01 | 2026-10-10 | 10 days
2.4 | Data Visualization (Heat maps, Honor Rolls, Reporting) |  | In Progress | 2026-10-11 | 2026-10-20 | 10 days
2.5 | Audit Trail System implementation (SF10, Grades, Notes) |  | In Progress | 2026-10-21 | 2026-10-30 | 10 days
3 | Mobile Application Development (Flutter) |  | In Progress
3.1 | Setup Riverpod, Dio Interceptors, and Hive Offline Engine |  | In Progress | 2026-09-09 | 2026-09-15 | 7 days
3.2 | Scaffold Global UI (Hamburger Menus, Deep Slate Theme) |  | In Progress | 2026-09-16 | 2026-09-20 | 5 days
3.3 | Adviser Workspace: Offline grid grading & locking flow |  | In Progress | 2026-09-21 | 2026-09-30 | 10 days
3.4 | Adviser Workspace: Neon toggle attendance & Outbox sync |  | In Progress | 2026-10-01 | 2026-10-08 | 8 days
3.5 | ADM Coordinator Hub: Kanban case pipeline & KPI overview |  | Not Started | 2026-10-09 | 2026-10-16 | 8 days
3.6 | Parent Portal: FCM Alerts, GitHub-style Heatmaps & Grades |  | Not Started | 2026-10-17 | 2026-10-23 | 7 days
3.7 | Student Dashboard: Schedule, Attendance Gauge & ADM Tasks |  | In Progress | 2026-10-24 | 2026-10-30 | 7 days
4 | Cross-Platform Integration |  | Not Started
4.1 | Connect Web grading with Mobile FCM locking alerts |  | Not Started | 2026-10-31 | 2026-11-04 | 5 days
4.2 | Sync Rule-Based Interventions across Web & Mobile ADM hubs |  | Not Started | 2026-11-05 | 2026-11-09 | 5 days
5 | Testing |  | Not Started
5.1 | Mobile Offline Sync Stress Testing & Web Integration Testing |  | Not Started | 2026-11-10 | 2026-11-16 | 7 days
5.2 | System Testing & User Acceptance Testing (UAT) |  | Not Started | 2026-11-17 | 2026-11-23 | 7 days
6 | Documentation |  | Not Started
6.1 | Chapters 1-3 Revision |  | Not Started | 2026-11-24 | 2026-11-25 | 2 days
6.2 | Chapters 4-5 Creation |  | Not Started | 2026-11-26 | 2026-11-27 | 2 days
6.3 | Final Manuscript & Defense Preparation |  | Not Started | 2026-11-28 | 2026-11-30 | 3 days